EFIC / IRB Milestones

START-UP ACTIVITIES – For NETT Spokes

The following resources have been developed to assist you with completing all milestone tasks.

- ESETT toolbox available at: www.ESETT.org

- ESETT Regulatory Parameters pdf

Instructions for acceptable documentation parameters, including unique circumstances, 1572’s,

deferrals, waivers, and documents that apply to more than one spoke (tasks: 3-4 & 8-10).

Available in WebDCU: ESETT > Toolbox > Project Documents

- CC Form Key pdf, and CC & PD Form Guide pdf

Instructions for completing CC and PD data-entry in ESETT WebDCU (tasks 5 & 6).

Available in WebDCU: ESETT > Toolbox > Project Documents

Task 1:

- Spoke: Submit CC and PD Materials to your NETT Hub liaison for review prior to IRB submission. If your IRB requires review of the Informed Consent & Assent (if applicable) at this phase of the submission, your site-specific versions should be submitted to your Hub for pre-approval now, prior to IRB submission, as well (see Task 7).

- Hub: Pre-review spoke material for any obvious deficiencies, prior to submitting spoke CC and PD materials to Deneil Harney (dkolk@umich.edu) for review/approval, prior to IRB submission. Initial CCC review will occur within 48 business hours of receipt.

NOTE: If the IRB requires review of the Informed Consent and Assent (if applicable) at this phase of the submission, the spoke version should be submitted to the CCC at ESETT-milestone@umich.edu for review/approval prior to returning it back to the spoke for submission to their IRB (see Task 7).

Task 2:

- Hub: Contact SDMC (connerc@musc.edu) to have any new spoke added to WebDCU.  Once this step has been completed you can assign the new spoke to ESETT in the database.

Task 3:

- Hub: Upload spoke EFIC plan IRB submission documentation into WebDCU for the spoke under the record titled: “EFIC Plan IRB Submission”.

Task 4:

- Hub: Upload spoke EFIC plan IRB approval documentation into WebDCU for the spoke under the record titled: “EFIC Plan IRB Approval”.

Task 5:

- Spoke/Hub: Complete CC activities and enter CC event data into WebDCU via the CC form.  All queries related to the CC forms must be reconciled for task eligibility. Contact Deneil Harney (dkolk@umich.edu) for review and approval.

Task 6:

- Spoke/Hub: Begin PD activities and enter PD event data into WebDCU via the PD form. PD activity will be ongoing throughout the trial, but sites should complete a form for each event completed prior to enrollment.  All data queries related to the PD forms must be reconciled for task eligibility. Contact Deneil Harney (dkolk@umich.edu) for review and approval.

Task 7:

- Spoke: Submit your Informed Consent/Assent documents to your NETT Hub liaison for review prior to submitting them to your IRB for their approval.

- Hub: Pre-review spoke consent materials for any obvious deficiencies, prior to submitting them to the NETT CCC at ESETT-milestone@umich.edu for review/approval.  Initial consent review will occur within 48 business hours of receipt.

Task 8:

- Spoke: Submit the full ESETT application to the IRB.  This application should include the results from Community Consultation, the final Protocol, and all Informed Consent Forms.

- Spoke/Hub:  Document proof of spoke IRB submission in WebDCU.  This application should include results from Community Consultation, the final Protocol, and Informed Consent Forms, etc.  Complete in WebDCU under the record titled: Full Study IRB Application Submission.

Task 9:

- Spoke/Hub: Upload the full application IRB approval letter into WebDCU for at least one participating NETT Hub/Spoke or PECARN Site.  The IRB approval letter should indicate approval of the current version of the protocol and acknowledge the review of your CC/PD results.  Complete in WebDCU under the record titled: Protocol v1 IRB Approval.

Task 10:

- Hub/Spoke: Reconcile all regulatory and training requirements in WebDCU for this Spoke.  Contact the CCC at ESETT-milestone@umich.edu for approval.

Task 11:

- Spoke/Hub: Arrange and complete a readiness call and be released to enroll by the CCC.  A spoke should plan a readiness call which corresponds with the completion of:  All study-staff training being complete, contracts finalized, and when the hub/spoke/site is ready to begin enrollment immediately.  Contact ESETT-milestone@umich.edu for more information and to set up your readiness call.

Contact the CCC at ESETT-milestone@umich.edu for more information and to set up your readiness call.  Two weeks’ notice is desirable; to coordinate a date and time that will work for everyone that needs to attend.  The date a spoke is released to enroll by the CCC in WebDCU will be used to verify the date this task was completed.