EFIC / IRB Milestones

START-UP ACTIVITIES – For NETT Spokes

Task 1:

- Spoke: Submit CC and PD Materials to your NETT Hub liaison for review prior to IRB submission. If your IRB requires review of the Informed Consent & Assent at this phase of the submission, your site-specific versions should be submitted to your Hub for pre-approval now as well (see Task 7).

- Hub: 	Pre-review spoke material for any obvious deficiencies, prior to submitting spoke CC and PD materials to Deneil Harney (dkolk@umich.edu) for review/approval, prior to IRB submissions. Initial CCC review will occur within 48 business hours of receipt.

NOTE: If the IRB requires review of the Informed Consent and Assent at this phase of the submission, the spoke version should be submitted to the CCC at ESETT-milestone@umich.edu for review/approval prior to returning it back to the spoke for submission to their IRB (see Task 7).

Task 2:

- Hub:	Contact SDMC (connerc@musc.edu) to have any new spoke added to WebDCU.  Once this step has been completed you can assign the new spoke to ESETT in the database.

Task 3:

- Hub: 	Upload spoke EFIC plan IRB submittal documentation into WebDCU for the spoke under the record titled: “ESETT EFIC Plan IRB Submittal”.

Task 4:

- Hub: 	Upload spoke EFIC plan IRB approval documentation into WebDCU for the spoke under the record titled: “ESETT EFIC Plan IRB Approval”.

Task 5:

- Spoke/Hub: Complete CC activities and enter associated CC results into WebDCU via the Community Consultation Summary (CCS) form in the ESETT WebDCU database.  All queries related to CCS data must be reconciled for task eligibility. After all the new events have been entered, contact Deneil Harney (dkolk@umich.edu) for approval.

Task 6:

- Spoke/Hub: Begin PD activities and enter related PD data into WebDCU via the Public Disclosure Summary (PDS) form in the ESETT WebDCU database. PD activity will be ongoing throughout the trial, but spokes should show results for events completed prior to beginning enrollment.  Queries related to PDS forms completed prior to enrollment in WebDCU must be reconciled for task eligibility. Contact Deneil Harney (dkolk@umich.edu) for approval.

Task 7:

- Spoke: Submit your Informed Consent/Assent documents to your NETT Hub liaison for review prior to submitting them to your IRB for their approval.

- Hub: 	Pre-review spoke consent materials for any obvious deficiencies, prior to submitting them to the NETT CCC at ESETT-milestone@umich.edu for review/approval.  Initial consent review will occur within 48 business hours of receipt.

Task 8:

- Spoke: Submit the full ESETT application to the IRB.  This application should include the results from Community Consultation, the final Protocol, and all Informed Consent Forms.

- Spoke/Hub: 	Document proof of spoke IRB submittal in NETT WebDCU.  This application should include results from Community Consultation, the final Protocol, and Informed Consent Forms.  Complete in WebDCU under the record titled: ESETT Full Study IRB Application Submittal.

Task 9:

- Spoke/Hub: Upload IRB full application approvals (including approval of completed CC/PD activities) into WebDCU.  This record should include the full application and its attachments (minus the consent/Assent forms, which reside elsewhere in WebDCU), the IRB approval letter, (indicating approval of v1 of the protocol and receipt of CC/PD activity results), and documentation of deferral to another IRB (if applicable).  Complete inWebDCU under the record titled: Protocol v1 IRB Approval.

Task 10:

- Hub/Spoke: Reconcile all regulatory and training requirements in WebDCU for this Spoke.  Contact the NETT CCC at ESETT-milestone@umich.edu for approval.

Task 11:

- Spoke/Hub: Arrange and complete a “Readiness Call” and be released to enroll by the CCC.  A spoke should plan a readiness call which corresponds with the completion of:  All study-staff training being complete, contracts finalized, and the spoke is ready to begin enrollment immediately.

Contact the NETT CCC at ESET-milestone@umich.edu for more information and to set up your readiness call.  Two weeks’ notice is desirable; to coordinate a date and time that will work for everyone that needs to attend.  The date a spoke is released to enroll by the CCC in WebDCU will be used to verify the date this task was completed.

The following resources have been developed to assist you with the above tasks:

- Instructions for acceptable documentation parameters, including unique circumstances, 1572’s,

deferrals, waivers, and documents that apply to more than one spoke.

NETT and ESETT Regulatory Document Approval Parameters for WebDCU pdf

Available in WebDCU: NETT > Toolbox > Project Documents

- Instructions for completing CC and PD data-entry in ESETT WebDCU (tasks 5 & 6 above).

CCS Form Guide & the ESETT Instruments – CCS Key pdf, and PDS Form Guide pdf.

Available in WebDCU: ESETT > Toolbox > Project Documents